## Color
PROJECT: CIVE 202 Project #3
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Lucas Lee
Project start date: | 2026-03-31 |  |  |  |  | March | [6 empty] | April | [27 empty] | May
Scrolling increment: | 0 | time axis 2026-03-31 to 2026-05-25
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2026-03-31 to 2026-05-25
Project Preparation
Download and Investigate Data | On Track | Lucas | 100% | 2026-02-27 | 3
Review NGSIM and NHTS codebooks | Low Risk | Lucas | 0% | 2026-02-27 | 3
Data Visualization
Comparison Bar Chart | On Track | Lucas | 100% | 2026-03-06 | 4
Histogram | On Track | Lucas | 100% | 2026-03-09 | 4
Boxplot | On Track | Lucas | 100% | 2026-03-12 | 4
Time-Series Plot 1 | On Track | Lucas | 100% | 2026-03-15 | 4
Time-Series Plot 2 | On Track | Lucas | 100% | 2026-03-18 | 5
Simulation Study
Time-Series Plot | On Track | Lucas | 100% | 2026-03-27 | 3
Documentation
Scope of Work | On Track | Lucas | 100% | 2026-02-27 | 7
Anotated Code Document | On Track | Lucas | 100% | 2026-03-21 | 10
Final Report | On Track | Lucas | 100% | 2026-03-21 | 10
To add more data, Insert new rows ABOVE this one